## PREP
PRE ITAS SERVICE PACK DEPLOYMENT
ID | PREPERATION | COMPLETED | DETAILS
P1 | Create Exec.zip Folder
P2 | Check Spinfo.dat - MUST MATCH REQUEST DETAILS
P3 | Rename Menu.exe
P4 | Rename Hivedome.Itas.Shell.exe
ID | STOP SERVICES | COMPLETED | DETAILS
P5 | ITAS Docman Server
P6 | ITAS Heritage Alerts Listener
P7 | ITAS Notifications
P8 | ITAS Server
P9 | WB (Weighbridge)
P10 | Other
ID | CLOSE OPEN APPLICATIONS | COMPLETED | DETAILS
P11 | Close open ITAS programs via Task Manager
P12 | Close open ITAS programs via Comp Manager
P13 | Close open Session via Comp Manager
ID | DISABLE OVERNIGHTS | COMPLETED | DETAILS
P14 | Check Windows Task Scheduler
P15 | Disable ITAS DEP if due to run during the deployment
ID | TAKE BACKUPS | COMPLETED | DETAILS
P16 | itas
P17 | ITAS-NG
P18 | Other Databases
PRE ITAS SERVICES UPDATE DEPLOYMENT
ID | PREPERATION | COMPLETED | DETAILS
P21 | Ensure latest version of Deployment Tool in place
P22 | Launch Deployment Tool
P23 | Login to the Deployment Tool
P24 | Select ITAS Services version to be deployed - MUST MATCH REQUEST DETAILS

## DEPLOYMENTS
DEPLOY ITAS SERVICE PACK INSTALL
ID | DEPLOYMENT | COMPLETED | DETAILS
D1 | Install ITAS Heritage Service Pack
D2 | Check ITAS Heritage Install Log To Ensure No 'Error'
D3 | Check ITAS Heritage Install Log To Ensure No 'Warning'
D4 | Check ITAS Heritage Install Log For 'Web Database updated'
DEPLOY ITAS SERVICES UPDATE
ID | DEPLOYMENT | COMPLETED | DETAILS
D5 | Run Deployment - Click Upgrade Button
D6 | Click <> PowerShell To View Details
D7 | Once Deployment Completed Ensure Install Log Present |  | If an install log is NOT created automatically, Click COPY
D8 | Close Deployment Tool

## COMPLETE
COMPLETE DEPLOYMENTS
ID | RESTART SERVICES | COMPLETED | DETAILS
C1 | Restart Stopped Services
C2 | Rename Menu.exe
ID | CHECK IIS | COMPLETED | DETAILS
C3 | Ensure all Application Pools are started
C4 | Ensure all Sites are started
ID | TIDY ITAS\INSTALL FOLDER | COMPLETED | DETAILS
C5 | Move installed service pack to Old SP Folder
C6 | Delete remaining service pack files
ID | ENABLE OVERNIGHTS | COMPLETED | DETAILS
C7 | Enable ITAS DEP
C8 | Run ITAS DEP if due to run during the deployment

## TD
TRADER DESKTOP
ID | TRADER DESKTOP TESTS | RESULT | DETAILS
TD1 | Launch Hivedome.Itas.Shell.exe as Administrator
TD2 | Run RegRefesh - Should Run Automatically?
TD3 | Enter email address - IF Prompted
ID | HELP
TD4 | Launch ABOUT ITAS - Check ITAS NG Version Information
TD5 | Launch TRADER DESKTOP HELP
TD6 | Ensure Site details appear in Header
ID | DATA ENTITIES
TD7 | Launch Data Entities
TD8 | Launch Physical Trades Grid
TD9 | Launch TRADE - Using Contract Ref Link
ID | FLYOUT MENU
TD10 | Launch Flyout Menu
TD11 | Launch A Menu Item
ID | TRADING ENTITIES
TD12 | Launch TRADE
TD13 | Launch CLI
TD14 | Launch INVENTORY - PROMAN/PROTANK etc. |  | If Licensed
TD15 | Launch WIP |  | If Licensed
TD16 | Launch TERM |  | If Licensed
ID | SMART PANEL
TD17 | Launch SMART PANEL
TD18 | Launch Menu Item - Ensure Details moves to top of History Tab
TD19 | Launch Field Help
TD20 | Launch Book Help
ID | STAR REPORTS - IF LICENSED
TD21 | Launch Star Reports
TD22 | Accounting Report
TD23 | Traffic Report
ID | TRADER DESKTOP TILES
TD24 | Launch TRADE - Ensure TRADE moves to top of History Tab
TD25 | Launch CLI - Ensure Account Number visible in CLI
ID | TRADER DESKTOP SHORTCUTS
TD26 | Open Trade (O + T)
TD27 | Fly Out Menu (F + M)

## DOCMAN
DOCMAN
ID | DOCMAN TESTS | RESULT | NOTES
DM1 | Launch DOCMAN from NAVIGATION PANEL
DM2 | Launch ITAS PERSONAL DOCUMENTS - Ensure Documents can be seen
DM3 | Launch COMPANY DOCUMENTS - Ensure Documents can be seen
DM4 | Open Contract - Using Contract ID Link
DM5 | Highlight Document Print and Export - Using Tick Box
DM6 | Select Print and Export
DM7 | Select Show Preview Pane - - Ensure dcoment contents can be seen
DM8 | Launch UNVERIFIED DOCUMENTS - Ensure Documents can be seen
DM9 | Launch UNINDEXED DOCUMENTS - Ensure Blue Config Message does not appear
DM10 | Launch ARCHIVED DOCUMENTS - Ensure Documents can be seen

## SETTINGS
SETTINGS MENU
ID | ITAS SETTINGS MENU TESTS | RESULT | NOTES
ID | SETTINGS MENU
SM1 | Launch SETTINGS MENU
SM2 | Check GF Items present
ID | TRADING ENTITY MANAGEMENT
SM3 | Launch TRADING ENTITY MANAGEMENT
SM4 | Launch S01
ID | SYSTEM SETTINGS
SM5 | Launch SYSTEM SETTINGS
SM6 | Launch Modules
SM7 | Check Services are Running
SM8 | Launch Active Users
SM9 | Check Release History
SM10 | Launch System Info
ID
SM11 | Launch User Admin
SM12 | Launch CMP
SM13 | Launch AUTH
SM14 | Launch MTM
SM15 | Launch Admin Console
SM16 | Launch ITAS WorkFlow Console

## ALERTS
ALERTS
ID | ITAS ALERTS TESTS | RESULT | NOTES
ID | MESSAGE USERS
A1 | Launch MESSAGE USERS
A2 | Select SEND MESSAGE TO ALL USERS
A3 | Add Subject
A4 | Send message with details of TD version installed
ID | ALERTS ADMIN - IF NO TEST ALERT EXISTS
A4 | Launch ALERTS ADMIN from SETTINGS MENU
A5 | Click on DATA ALERTS
A6 | Create Test Alert - Use CLI STATIC TABLE & chr20_testaudit column
A7 | Switch on the Test Alert
ID | MY ALERTS
A8 | Launch MY ALERTS
A9 | Subscribe to new Test Alert
ID | ALERTS ADMIN - IF NO TEST ALERT EXISTS
A10 | Launch ALERTS ADMIN from SETTINGS MENU
A11 | Click on ALERT SYSTEM TEST
A12 | Ensure that at least one company is selected
A13 | Click RUN TEST

## SERVICES
WEB SERVICES
ID | ITAS WEBSERVICES TESTS | RESULT | NOTES
ID | EVENTS
WS1 | Browse to https://APPSERVERNAME:5710/swagger
ID | ITAS API TESTS
WS2 | Browse to https://APPSERVERNAME:5720
ID | ITAS WEBPORTAL TESTS
WS3 | Browse to https://APPSERVERNAME:5726 |  |  | `
ID | ITAS DATAPORTAL TESTS
WS4 | Browse to https://APPSERVERNAME:5727
ID | ITAS DATA CATALOG TESTS
WS5 | Browse to https://APPSERVERNAME:5731
ID | ITAS WORKFLOW TESTS
WS6 | Browse to https://APPSERVERNAME:5740
WS7 | Browse to https://APPSERVERNAME:5740/swagger
ID | ITAS IDENTITY SERVER TESTS
WS8 | Browse to https://APPSERVERNAME:5750
ID | ITAS ODATA SERVICE TESTS
WS09 | Browse to https://APPSERVERNAME:5760
ID | ITAS DOCUMENT SERVICE TESTS
WS10 | Browse to https://APPSERVERNAME:5770/swagger
ID | ITAS GRAPH SERVICE TESTS
WS11 | Browse to https://APPSERVERNAME:5780/swagger
ID | ITAS TASKS SERVICE TESTS
WS12 | Browse to https://APPSERVERNAME:5800/swagger
ID | ITAS WorkFlow SERVICE TESTS
WS13 | Browse to https://APPSERVERNAME:5810/swagger

## DP
DATAPORTAL
ID | ITAS WEBPORTAL TESTS | RESULT | NOTES
DP1 | Browse to https://APPSERVERNAME:5727
ID | DATA
DP2 | Launch DATA Views
DP3 | Expand Client Accounts
DP5 | View All Acounts View
DP6 | Expand Physical Trades
DP7 | View All Contracts View
ID | DOCS
DP8 | Launch Docs Views
DP9 | Expand Company Documents
DP10 | View All Documents
ID | REPORTS
DP11 | Launch Reports Views
DP12 | Launch A Report

## REPORTS
IF REPORTING FUNCTIONALITY IS LICENSED
ID | REGREFRESH | RESULT | NOTES
R1 | Run Regrefresh on Reporting DB SQL Server
ID | REPORTING DATABASE TESTS |  | NOTES
R2 | Launch REPORTS ADMIN > MANUAL DATA EXPORT
R3 | Trigger a Manual Export
R4 | Check SCHEDULED EXPORT ACTIVITY - Check export job STATUS
R5 | Check EXPORT HISTORY for Completed Export Job
IF REPORT FACTORY IS LICENSED
ID | REPORT FACTORY TESTS | RESULT | NOTES
RF1 | Launch GF > RFREQ
RF2 | Trigger a Mock Request - Output to screen
RF3 | Ensure Report appears on Screen
IF DATA FACTORY IS LICENSED
ID | REPORT FACTORY TESTS | RESULT | NOTES
DF1 | Launch GF > DFREQ
DF2 | Trigger a Custom Request
DF3 | Check SCHEDULED EXPORT ACTIVITY - Check export job STATUS
DF4 | Check EXPORT HISTORY for Completed Export Job

## POST
DEPLOY ITAS SERVICE PACK INSTALL
ID | DEPLOYMENT | COMPLETED | DETAILS
P1 | Send Release Notes To Client
P2 | Complete Deployment Schedule Task
P3 | Add PDCL To Deployment Schedule Task
P4 | Add Zendesk Ticket To Deployment Schedule Task
P5 | Update Version Installed In Notion
P6 | Update Deployment Issues In Notion If Needed

## MASTER DATA
ID | TRADER DESKTOP VERSION | YES/NO | RESULT | SQL BACKUP TAKEN
1 | 8.19.0 | YES | PASS | Backup Taken By Hivedome
2 | 8.18.2 | NO | FAIL | Backup Taken By Client
3 | 8.18.1 | N/A | Not Licensed | Customer Requested No Backup
4 | 8.18.0 |  | N/A | Customer Requested Over Night Backup To Be Used
5 | 8.17.2 |  |  | UAT Server
6 | 8.17.1
7 | 8.17.0
8 | 8.16.2
9 | 8.16.1
10 | 8.16.0
11 | 8.15.1
12 | 8.15.0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50